## Risk Register
RISK REGISTER
REF ID | RISK | RISK Description | RISK Impact | RISK CATEGORY | PROBABILITY 1 – 3 | IMPACT 1 – 3 | PI SCORE Prob x Impact | Response Strategy
R1 | Malware and Ransomware | Potential infiltration of malicious software | Data loss, financial loss, operations can be disrupted | Cybersecurity Risk | 2 | 3 | 6 | Make sure your software is updated, make sure employees are trained to recognize malware
R2 | Phishing attacks | Email attacks that try to trick employees by getting them to click a link or virus | Unauthorized access, data breaches | Cybersecurity Risk | 3 | 3 | 9 | Multi factor authentication, train employees to detect those emails, email filtering
R3 | Hardware failures | Breakdown of the hardware can lead to network downtime | Disruption of operations, data loss | Infrastructure Risk | 2 | 2 | 4 | Conduct regular maintenance on the hardware, have a backup and a recovery plan
R4 | Software Vulnerabilities | If your software is outdated it could lead to unauthorized access or systems to be compromised | Data breaches, system downtime | Infrastructure Risk | 2 | 3 | 6 | Make sure your software is updated, conduct vulnerability assessments, and monitor threats
R5 | Unstuffiness Training | The lack of awareness and training leading to security lapses by employees | Data loss, system outages | Operational Risks | 2 | 2 | 4 | You could conduct cybersecurity training programs and classes and establish clear security policies
R6 | Human Error | Mistakes made by employees can lead to data breaches or any other security problems | Data loss, system outages | Operational Risks | 2 | 2 | 4 | Provide ongoing training, two factor authentication, and conduct regular security checks.
R7 | Vendor Security | There can be a lot of security vulnerabilities because of third party vendors or service providers | Data breaches, sensitive information can be compromised | Third Party Risks | 2 | 2 | 4 | Monitor vendors and third parties and establish contractual security requirements
R8 | Supply Chain Attacks | These are cyberattacks that target a supply chain, potentially impacting the network | Supply chain data is compromised and your operations get disrupted | Third Party Risks | 1 | 2 | 2 | Make sure you monitor and secure the supply chain and collaborate with suppliers on cybersecurity practices
R9 | Non-Compliance | Failure to comply with industry regulations or data protection laws | Legal consequences and financial penalties | Compliance and Legal Risks | 2 | 2 | 4 | Make sure you are informed about the regulatory changes and implement measures to address compliance gaps
R10 | Legal Consequences | Legal action or fines that resulted from data breaches or non-compliance with regulations | Financial losses, a bad look on the business | Compliance and Legal Risks | 1 | 2 | 2 | Maintain documentation to demonstrate compliance efforts and make sure you have a strong incident response plan
R11 | Inadequate Scalability | The network infrastructure may not be able to scale effectively as the company grows | Vulnerabilities are increased and the performance of the network could decline | Scalability Risks | 2 | 2 | 4 | Make sure you are actively trying to better your network and always planning for future scalability
R12 | Performance Issues | Your network can decline in performance because of the increased traffic and load | Productivity declines and users will be unhappy | Scalability Risks | 2 | 2 | 4 | Make sure that you conduct regular performance tests and invest in additional resources as you need to
R13 | Limited Budget | Having unstuffiness funds in order to upgrade security measures | Security programs and shy hardware can be outdated | Resource Constraints | 3 | 3 | 9 | Make sure that you are sticking to your budget and explore cost effective security solutions
R14 | Lack of skilled Personnel | Could have a shortage of employees with cybersecurity expertise | Vulnerabilities will be increased and inadequate responses | Resource Constraints | 3 | 3 | 9 | Increase the security budget in order to hire the correct amount of people and invest in training programs
R15 | Inadequate Incident Response Plan | Lack of a well defined plan to respond to any security breaches or incidents | Delayed responses and damages if anything happened can be increased | Incident Response Risks | 2 | 2 | 4 | Develop a strong and up to date incident response plan and conduct training simulations
R16 | Response Time | Delays in identifying and responding to any security breaches and incidents | Increased damage and prolonged disruptions | Incident Response Risks | 2 | 2 | 4 | Could implement and monitor alerting systems and conduct regular drills in order to improve response times
R17 | Changing Compliance Landscape | Regulations are always evolving so you need to dust to security measures | Challenges with compliance and legal consequences | Regulatory Changes | 2 | 2 | 4 | Make sure you and the people that work with your network are informed about regulatory changes and always adapt.
R18 | Unexpected Compliance Challenges | You could have challenges with adapting to new compliance requirements | This could also result in legal consequences | Regulatory Changes | 1 | 1 | 1 | Try to establish a compliance monitoring program and make sure you are willing to adapt
R19 | Social Engineering Attacks | These attempt to manipulate employees through social engineering attacks | Data breaches and unauthorized access | Social engineering Risks | 2 | 3 | 6 | Make sure your employees are being trained regularly or social engineering awareness and implement strict access controls
R20 | Impersonation | When unauthorized individuals gain access through the impersonation of a legitimate user | Unauthorized access, data breaches | Social engineering Risks | 1 | 1 | 1 | Make sure you have multi factor authentication and establish clear identify verification processes
0
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.